## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project (Cyber Risk Assessment System) | MUST HAVE | No dependency | Gayathri | 3- Completed
S1 | S1 | US-001 | Workflow creation and project planning | MUST HAVE | Lucid chart | Gayathri | 3- Completed
S2 | S2 | US-001 | Requirement analysis and use case preparation | MUST HAVE | No dependency | Gayathri | 3- Completed
S2 | S2 | US-001 | Design system architecture and modules | SHOULD HAVE | Research papers | Gayathri | 3- Completed
S3 | S3 | US-001 | Implement Nmap scanning module | MUST HAVE | NMAP tool | Gayathri | 3- Completed
S4 | S4 | US-001 | Develop database (SQLITE) for storing scan results | MUST HAVE | SQlite | Gayathri | 3- Completed
S5 | S5 | US-001 | Develop streamlit dashboard UI | MUST HAVE | Streamlit | Gayathri | 3- Completed
S6 | S6 | US-001 | Implement risk scoring and severity calculation | SHOULD HAVE | Python logic | Gayathri | 3- Completed
S7 | S7 | US-001 | Integrate VirusTotal API for threat intelligence | SHOULD HAVE | virustotal API | Gayathri | 3- Completed
S8 | S8 | US-001 | Implement report generation and email alert system | MUST HAVE | SMTP,FPDF | Gayathri | 3- Completed
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
--
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 75 | 22 | 12 | 11 | 9 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Project introduction and setup | 2026-02-09 | 2026-02-10 | Gayathri | Build | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Workflow creation | 2026-02-10 | 2026-02-12 | Gayathri | Design | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Requirement analysis | 2026-02-12 | 2026-02-15 | Gayathri | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | System design | 2026-02-15 | 2026-02-18 | Gayathri | Coding | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Nmap scanning implementation | 2026-02-18 | 2026-02-22 | Gayathri | Coding | 3- Completed | 12 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Database integration | 2026-02-22 | 2026-02-25 | Gayathri | Design | 3- Completed | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Streamlit dashboard creation | 2026-02-25 | 2026-02-28 | Gayathri | Design | 3- Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | Risk scoring logic | 2026-03-01 | 2026-03-06 | Gayathri | Coding | 3- Completed | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 9 | virustotal API integration | 2026-03-06 | 2026-03-18 | Gayathri | Integration Test | 3- Completed | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 10 | Report generation & email alerts | 2026-03-18 | 2026-03-27 | Gayathri | Design | 3- Completed | 8 | 3 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9/15/2016 or 15-Sep-2016
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9/15/2016 or 15-Sep-2016
Note on I3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the total task estimated in hours for all the user stories
Note on J3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 1 work
Note on K3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 2 work
Note on L3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 3 work
Note on M3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 4 work
Note on N3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 5 work
Note on O3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 6 work
Note on P3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 7 work
Note on Q3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 8 work
Note on R3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 9 work
Note on S3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 10 work
Note on T3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 11 work
Note on U3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 12 work
Note on V3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 13 work
Note on W3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity in project requirements | Discussed with mentor and clarified requirements
Sprint 1 | Day 5 | confusion in workflow and architecture design | conducted brainstorming and finalized workflow
Sprint 2 | Day 10 | difficulty in identifying system modules | Researched online resources and documentation
Sprint 2 | Day 14 | Issue in designing system modules | Reviewed design with mentor and improved structure
Sprint 2 | Day 18 | Errors in Nmap scanning implementation | Debbuged code and referred documentation
Sprint 3 | Day 22 | Database connection issues | Fixed SQlite integration errors
Sprint 4 | Day 28 | UI alignment issues in streamlit dashboard | Adjusted layout and improved UI design
Sprint 4 | Day 32 | Difficulty in risk score calculation logic | Optimiszed formula and tested outputs
Sprint 5 | Day 38 | API integration errors | Debbuged API calls and handled responses
Sprint 5 | Day 45 | Email alerts not sending properly | Fixed SMTP configuration

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-09-03 | 18/3/26 | Gayathri | UI testing early | Unclear planning | Attending meeting daily | Scheduled review sessions with mentor
2 | Sprint 2 | 19/3/26 | 2026-01-03 | Gayathri | Proper time scheduling | delaying tasks | Testing modules regularly | Achieved python kit completion on time
3 | Sprint 3 | 2026-02-03 | 13/3/26 | Gayathri | Proper API testing | incorrect configuartions | validating API responses | Performed continous testing during development phases
4 | Sprint 4 | 14/3/26 | 24/3/26 | Gayathri | testing email configs early | last minute UI fixes | Monitoring system performance | Optimized queries and improved execution time